## Start here
SMBH Consulting ¦ Knowledge Centre
Risk assessment template
A risk register with a 5 × 5 likelihood and consequence matrix, ratings and action tracking.
How to use this workbook
1 | Read the Scales sheet so everyone rates likelihood and consequence the same way.
2 | On the Risk register sheet, list each risk as "event, cause, effect", for example "Loss of customer data from a phishing attack, leading to notification costs and lost trust".
3 | Rate likelihood (1 to 5) and consequence (1 to 5) as things stand today with your existing controls. The rating (likelihood × consequence) and level calculate automatically.
4 | For High and Extreme risks, record further action, an owner and a due date. Re-rate the risk after the action is done (residual rating).
5 | Review the register at least quarterly, and whenever something changes: a new product, a new site, a new system, a near miss or an incident.
6 | Work health and safety risks have specific legal duties under your state or territory WHS laws. Use this register alongside, not instead of, your WHS obligations.
Shaded yellow cells are inputs. Everything else is calculated by formulas; avoid typing over them.
SMBH Consulting ¦ smbhconsulting.com.au ¦ Version 1.0, updated 2026-11-06. General information only, not financial, legal or tax advice. Check current rules with the ATO, Fair Work or a registered adviser.

## Scales
SMBH Consulting ¦ Knowledge Centre
Rating scales
Agree these definitions with your team. Adjust the dollar amounts to suit the size of your business.
Score | Likelihood | Description
1 | Rare | Could happen only in exceptional circumstances (less than once in 10 years).
2 | Unlikely | Could happen at some time (once in 5 to 10 years).
3 | Possible | Might happen (once in 1 to 5 years).
4 | Likely | Will probably happen (about once a year).
5 | Almost certain | Expected to happen (several times a year).
Score | Consequence | Description
1 | Insignificant | Cost under $1,000; no injury; no customer impact.
2 | Minor | Cost $1,000 to $10,000; first aid injury; brief disruption to a few customers.
3 | Moderate | Cost $10,000 to $50,000; medical treatment; a day or more of disruption; a complaint to a regulator.
4 | Major | Cost $50,000 to $250,000; serious injury; loss of a key customer; regulatory action.
5 | Severe | Cost over $250,000; fatality or permanent injury; business may not survive.
Rating | Level | Expected response
15–25 | Extreme | Act now. Owner-level attention, treatment plan within days.
10–14 | High | Treatment plan with owner and due date within a month.
5–9 | Medium | Manage with routine controls and monitor at each review.
1–4 | Low | Accept and monitor.
SMBH Consulting ¦ smbhconsulting.com.au ¦ Version 1.0, updated 2026-11-06. General information only, not financial, legal or tax advice. Check current rules with the ATO, Fair Work or a registered adviser.

## Risk register
SMBH Consulting ¦ Knowledge Centre
Risk register
Yellow cells are inputs. Rating = likelihood × consequence. Level: Extreme 15+, High 10–14, Medium 5–9, Low 1–4.
ID | Risk (event, cause, effect) | Category | Existing controls | Likelihood (1–5) | Consequence (1–5) | Rating | Level | Further action | Owner | Due date | Status | Residual likelihood | Residual consequence | Residual rating | Residual level
| Phishing email leads to stolen banking credentials and fraudulent payments | Cyber and IT | Staff awareness emails; bank dual approval over $5,000 | 4 | 4 |  |  | Turn on multi-factor authentication for email and banking; quarterly phishing training | Operations manager | 2026-12-15 | In progress | 2 | 4
| Loss of our largest customer (30% of revenue) causes a cash shortfall | Financial | Account reviews twice a year | 3 | 4 |  |  | Diversify: target three new accounts of similar size this financial year | Owner | 2027-06-30 | Not started | 3 | 3
| Key supplier stops trading, delaying jobs for weeks | Supply chain | Informal second supplier | 2 | 3 |  |  | Formalise a backup supplier agreement and keep two weeks of critical stock | Purchasing lead | 2027-02-28 | Not started | 2 | 2
| Customer data disclosed in error, triggering privacy obligations | Legal and compliance | Privacy policy; role-based access in CRM | 2 | 4 |  |  | Document a data breach response plan aligned with the Notifiable Data Breaches scheme | Owner | 2027-01-31 | Not started | 2 | 3
| Manual handling injury in the warehouse | Work health and safety | Trolleys provided; induction covers lifting | 3 | 3 |  |  | Install a pallet jack; refresher training; incident reporting process | Warehouse supervisor | 2026-12-01 | In progress | 2 | 3
| Owner unavailable for an extended period with no one able to approve payments | People | None | 2 | 4 |  |  | Second authorised signatory; document key processes | Owner | 2027-03-31 | Not started | 2 | 2

## Matrix
SMBH Consulting ¦ Knowledge Centre
Risk matrix and summary
Ratings for each likelihood and consequence pair, and a count of current risks by level.
Likelihood ↓ / Consequence → | 1 Insignificant | 2 Minor | 3 Moderate | 4 Major | 5 Severe
5 Almost certain
4 Likely
3 Possible
2 Unlikely
1 Rare
Level | Current | Residual
Extreme
High
Medium
Low
Open actions (not Done or Accepted)
SMBH Consulting ¦ smbhconsulting.com.au ¦ Version 1.0, updated 2026-11-06. General information only, not financial, legal or tax advice. Check current rules with the ATO, Fair Work or a registered adviser.